## Sheet1
ITEC4450 Project Timeline and Tracking Group: ClownFiesta Group Member: Eric D. Kim, Taylor Brust, Nate Sims, Miguel Antigua
1. Choose a collaboration tool: Dropbox; google docs or others 2. Prioritize the task 3. Check progress with each group member every other day to make sure everyone is on the same page 4. Update this tracking file any time necessary ( you may add new tasks, update task status, offer help for group members) 5. Don't forget testing as a major task, and list the task in the excel 6. This file is a general template, feel free to add columns to address your group issue
Note from instructor: do not just list the issue here, approach your team members and get it solved; bottom line, try to complete the task on time
| Task | plan to be completed by | Responsible party | Task Status log (notes and comments)
1 | discuss the overall UI design and structure of the website , and itemize tasks | 2016-09-20 | Everyone | Build a template (prototype)
2 | Home page | 2016-09-20 | Miguel
3 | student registration page | 2016-09-20 | Nate
4 | Student home page(maybe other pages; list the file name if you have other pages) | 2016-09-20 | Nate
5 | Volunteer registration page | 2016-09-20 | Eric
6 | Volunteer home page(maybe other pages; list the file name of each page) | 2016-09-20 | Eric
7 | admin home page(maybe other pages) | 2016-09-20 | Taylor
8 | complete static pages | 2016-09-24 | Everyone | Attach all pages
9 | Help/Support/Contact Page | 2016-09-20 | Miguel
10 | Design Last | 2016-09-28 | Everyone | Come up with a plesaing UI
| End of Phase 2 | 2016-10-02